## ProductBacklog
PRODUCT BACKLOG
SPRINT BACKLOG | US ID | BACKLOG ITEM |  |  | PRIORITY | RESPONSIBLE | ESTIMATE DATE | REMARKS
|  | AS A/AN | I WANT TO | SO THAT
1 | SB1/US1 | game developer | Log in securely using my credentials | my progress is saved. | 1 | IK
1 | SB1/US2 | game developer | customize my profile settings | my gaming experience is personalized. | 1 | KV
1 | SB1/US3 | game developer | easily navigate through the game menus | I can quickly start playing. | 1 | JS
1 | SB1/US4 | game developer | create and customize my in-game character | I can represent myself in the game world. | 1 | IK
1 | SB1/US5 | game developer | a tutorial to guide me through basic controls and gameplay | I can understand how to play | 1 | KV
1 | SB1/US6 | game developer | want responsive and intuitive controls | I can enjoy smooth gameplay. | 1 | JS
1 | SB1/US7 | game developer | adjust graphic settings for optimal performance | the game runs smoothly on my device. | 1 | IK
1 | SB1/US8 | game developer | adjust sound settings for an immersive experience | so that the audio complements the gameplay | 1 | KV
1 | SB1/US9 | game developer | save and load my game progress | I can continue playing from where I left off. | 1 | JS
1 | SB1/US10 | game developer | join or create a lobby | I can play with friends or other players. | 1 | IK
1 | SB1/US11 | game developer | an in-game chat system | I can communicate with other players during gameplay. | 1 | KV
1 | SB1/US12 | game developer | earn achievements for completing specific tasks | I can showcase my gaming skills. | 1 | JS
1 | SB1/US13 | game developer | access to a leaderboard | to see where I rank compared to other players. | 1 | IK
1 | SB1/US14 | game developer | browse and purchase in-game items from a virtual store | I can enhance my gaming experience. | 1 | KV
1 | SB1/US15 | game developer | engaging quests with rewards | I have continuous challenges and goals in the game. | 1 | JS
1 | SB1/US16 | game developer | to provide feedback on the game | developers can improve the overall gaming experience. | 1 | IK
1 | SB1/US17 | game developer | I want the option to reset all settings to default | can start fresh with the default configuration. | 1 | KV
1 | SB1/US18 | game developer | the game to have features like subtitles and color-blind options | I can enjoy the game fully. | 1 | JS
1 | SB1/US19 | game developer | game's user interface to be responsive on different devices | I can play on various platforms seamlessly. | 1 | IK
1 | SB1/US20 | game developer | different game modes (single-player, multiplayer, co-op) | I can choose the type of gaming experience I prefer. | 1 | KV
1 | SB1/US21 | game developer | I want the game to have dynamic weather effects that influence gameplay | I can experience a more immersive environment. | 1 | JS
1 | SB1/US22 | game developer | I want the option for gesture-based controls | I can interact with the game using natural movements. | 1 | IK
1 | SB1/US23 | game developer | the ability to control certain aspects of the game using voice commands | I can have a hands-free gaming experience. | 1 | KV
1 | SB1/US24 | game developer | I want the in-game chat system to translate messages in real-time | I can communicate with players who speak different languages. | 1 | JS
1 | SB1/US25 | game developer | the game difficulty to adjust dynamically based on my performance | I am constantly challenged but not overwhelmed. | 1 | IK
1 | SB2/US1 | game developer | immersive haptic feedback through the controller | I can feel the impact of in-game actions. | 1 | KV
1 | SB2/US2 | game developer | I want the game to support virtual reality | I can experience a more immersive gaming environment. | 2 | JS
1 | SB2/US3 | game developer | the in-game environment to react to my actions | I can feel more engaged with the virtual world. | 2 | IK
1 | SB2/US4 | game developer | the game to have a realistic day-night cycle | I can experience different atmospheres during gameplay. | 2 | KV
1 | SB2/US5 | game developer | my choices in the game to impact the storyline and gameplay | I can have a personalized gaming experience. | 2 | JS
1 | SB2/US6 | game developer | random events to occur during gameplay | each gaming session feels unique and unpredictable. | 2 | IK
1 | SB2/US7 | game developer | the option to have in-game companions with unique abilities | I can strategize and tackle challenges together. | 2 | KV
1 | SB2/US8 | game developer | certain in-game challenges and events to be influenced by weather conditions | I need to adapt my strategy accordingly. | 2 | JS
1 | SB2/US9 | game developer | the tutorial to adapt based on my progress | I can learn the game mechanics at my own pace. | 2 | IK
1 | SB2/US10 | game developer | to use hand gestures to interact with the virtual world | I can have a more immersive experience. | 2 | KV
1 | SB2/US11 | game developer | the camera angles to change dynamically during gameplay | enhance cinematic moments and provide different perspectives. | 2 | JS
1 | SB2/US12 | game developer | my game progress to sync across different platforms | I can seamlessly switch between devices. | 2 | IK
1 | SB2/US13 | game developer | the game to have immersive soundscapes that change based on the in-game environment | to enhance the overall gaming experience. | 2 | KV
1 | SB2/US14 | game developer | the game to have realistic physics | in-game interactions and movements feel natural. | 2 | JS
1 | SB2/US15 | game developer | hidden Easter eggs and references in the game | can discover and enjoy additional content. | 2 | IK
1 | SB2/US16 | game developer | the AI opponents to adapt their strategies and difficulty based on my gameplay style | each encounter remains challenging. | 2 | KV
1 | SB2/US17 | game developer | the game to present optional in-game challenges with rewards | I can test my skills and earn additional benefits. | 3 | JS
1 | SB2/US15 | game developer | live in-game events that occur at specific times, providing unique challenges and rewards | I can participate in community-driven experiences. | 3 | IK
1 | SB2/US15 | game developer | the ability to customize control mappings and button | layouts to suit my preferences and accessibility needs | 3 | KV
1 | SB2/US15 | game developer | I want my story choices to have immediate consequences in the game world | affecting relationships and plot twists | 3 | JS
1 | SB2/US15 | game developer | the ability to create and share custom levels or scenarios with the community | to expand the game's content. | 3 | IK
1 | SB2/US15 | game developer | an interactive map within the game | I can easily navigate and plan my in-game activities. | 3 | KV
1 | SB2/US15 | game developer | I want a dynamic dialogue system where NPC responses change | based on my character's actions and choices. | 3 | JS
2 | SB2/US15 | game developer | to initiate the game controller system | I can start using AI-powered controls. | 3 | IK
2 | SB2/US15 | game developer | o calibrate the system for my hand gestures | it accurately recognizes my movements. | 3 | KV
2 | SB2/US15 | game developer | to configure voice commands, | I can control the game using my voice | 3 | JS
2 | SB2/US15 | game developer | to personalize gesture-based controls, | they suit my gaming style. | 3 | IK
2 | SB2/US15 | game developer | to customize voice commands | I can give specific instructions to the system. | 3 | KV
2 | SB2/US15 | game developer | to ensure the system accurately detects my hand gestures, | that my in-game actions are precise. | 3 | JS
2 | SB2/US15 | game developer | to change the voice command settings | the system adapts to my voice. | 3 | IK
2 | SB2/US15 | game developer | to test gesture controls in a controlled environment | so that I can fine-tune the system. | 4 | KV
2 | SB2/US15 | game developer | to set up the system for a specific game | it's optimized for that game's controls. | 4 | JS
2 | SB2/US15 | game developer | o create a new game profile | I can easily switch between games | 4 | IK
2 | SB2/US15 | game developer | to establish gestures for basic in-game actions (e.g., move forward, jump) | I can control my character seamlessly | 4 | KV
2 | SB2/US15 | game developer | to implement voice commands for specific game actions (e.g., cast a spell, reload), | I can play the game more intuitively. | 4 | JS
2 | SB2/US15 | game developer | to ensure the system's stability | it doesn't crash during gameplay. | 4 | IK
2 | SB2/US15 | game developer | to set up automated gameplay | the system can assist me with routine tasks. | 4 | KV
2 | SB2/US15 | game developer | to configure the chatbot companion's personality | it aligns with my preferences. | 4 | JS
2 | SB2/US15 | game developer | to integrate the chatbot into the game | it can provide in-game tips and guidance. | 4 | IK
2 | SB2/US15 | game developer | to test the chatbot's responses, | they are helpful and engaging during gameplay. | 4 | KV
2 | SB2/US15 | game developer | to enable voice control for the chatbot, | I can interact with it through voice commands. | 4 | JS
2 | SB2/US15 | game developer | o improve the chatbot's natural language processing | it understands my queries better. | 4 | IK
2 | SB2/US15 | game developer | to set the chatbot to respond with jokes and humor | it adds fun to my gaming experience. | 4 | KV
2 | SB2/US15 | game developer | to verify that the chatbot does not disrupt gameplay | t enhances, rather than distracts from, the experience. | 4 | JS
2 | SB2/US15 | game developer | to ensure that the chatbot's responses are contextually relevant | it provides meaningful assistance. | 4 | IK
2 | SB2/US15 | game developer | to test the overall system with different games | it works well across various gaming genres. | 4 | KV
2 | SB2/US15 | game developer | o measure the system's response time | it's quick and doesn't introduce lag. | 4 | JS
2 | SB2/US15 | game developer | to assess the system's accuracy in recognizing hand gestures, | it enhances gameplay. | 4 | IK
2 | SB2/US15 | game developer | to evaluate the speech recognition's accuracy | voice commands are executed correctly. | 4 | KV
2 | SB2/US15 | game developer | to fine-tune the gesture recognition model | it becomes even more accurate. | 4 | JS
2 | SB2/US15 | game developer | to enhance the voice recognition model | it better understands my commands. | 4 | IK
2 | SB2/US15 | game developer | to create a tutorial for users, | they can easily set up and use the system. | 4 | KV
2 | SB2/US15 | game developer | I want to document the entire project | future reference and troubleshooting. | 4 | JS
2 | SB2/US15 | game developer | to optimize the system's resource usage | it doesn't overload my computer. | 4 | IK
2 | SB2/US15 | game developer | to improve the system's error handling | it gracefully recovers from unexpected issues. | 4 | KV
2 | SB2/US15 | game developer | to create a user-friendly interface for configuring settings | users find it intuitive. | 4 | JS
2 | SB2/US15 | game developer | to test the system with different hardware configurations | it's compatible with a wide range of setups. | 4 | IK
2 | SB2/US15 | game developer | to add support for multiple languages in the chatbot, | it's accessible to a global audience. | 1 | KV
2 | SB2/US15 | game developer | to implement a user feedback system | users can report issues and suggest improvements. | 1 | JS
2 | SB2/US15 | game developer | to continuously update the system based on user feedback | it evolves with user needs. | 1 | IK
2 | SB2/US15 | game developer | to integrate a help center within the system | users can access documentation and support easily. | 1 | KV
2 | SB2/US15 | game developer | to ensure the system is compatible with popular gaming platforms (e.g., PC, console) | it reaches a broad audience. | 1 | JS
2 | SB2/US15 | game developer | to conduct user testing to gather feedback on the gaming experience | it can be further improved. | 1 | IK
2 | SB2/US15 | game developer | to conduct performance testing to identify bottlenecks | to identify bottlenecks and optimize the system. | 1 | KV
2 | SB2/US15 | game developer | to improve the system's error handling | it gracefully recovers from unexpected issues. | 1 | JS
2 | SB2/US15 | game developer | to add a user profile system | multiple users can have personalized settings. | 1 | IK
2 | SB2/US15 | game developer | to enhance the system's security | o protect user data and privacy. | 1 | KV
2 | SB2/US15 | game developer | to explore the possibility of integrating the system | the system with virtual reality (VR) gaming. | 1 | JS
2 | SB2/US15 | game developer | to create a mobile app version of the system | I can control games on my phone. | 2 | IK
2 | SB2/US15 | game developer | to conduct stress testing | ensure the system can handle high-demand scenarios. | 2 | KV
2 | SB2/US15 | game developer | to explore partnerships with game developers | seamless integration of the system with their games. | 2 | JS
2 | SB2/US15 | game developer | to create a comprehensive user manual | to guide users through the setup and customization process. | 2 | IK
2 | SB2/US15 | game developer | to optimize the system's resource usage | it runs smoothly on a wide range of hardware. | 2 | KV
2 | SB2/US15 | game developer | to test the system's compatibility | various operating systems (Windows, macOS, Linux). | 2 | JS
2 | SB2/US15 | game developer | to implement a tutorial mode within games | to help new users get acquainted with the system. | 2 | IK
2 | SB2/US15 | game developer | to conduct A/B testing to compare the system's performance | to compare the system's performance against traditional gaming controls. | 2 | KV
2 | SB2/US15 | game developer | to develop a marketing strategy | to promote the system and reach a larger user base. | 2 | JS
2 | SB2/US15 | game developer | to create a support portal where users | users can find troubleshooting guides and FAQs. | 2 | IK
2 | SB2/US15 | game developer | to explore the feasibility of integrating | the system with popular gaming consoles. | 2 | KV
2 | SB2/US15 | game developer | to improve the system's natural language understanding | understanding by using advanced NLP models. | 2 | JS
2 | SB2/US15 | game developer | to conduct usability testing with a diverse group of users | to ensure accessibility and inclusivity. | 2 | IK
2 | SB2/US15 | game developer | to integrate the system with cloud gaming services | for enhanced accessibility. | 2 | KV
2 | SB2/US15 | game developer | to optimize the system for low-latency connections | ensuring a seamless online gaming experience. | 2 | JS
2 | SB2/US15 | game developer | to create an API for game developers | to easily integrate the system into their games. | 3 | IK
2 | SB2/US15 | game developer | to implement a reporting system for users | to provide feedback and report issues directly within the system. | 3 | KV
2 | SB2/US15 | game developer | to expand the chatbot's capabilities to provide in-depth game | to provide in-depth game information and strategies. | 3 | JS
2 | SB2/US15 | game developer | to explore the potential of using machine learning | to predict user gestures and voice commands. | 3 | IK
2 | SB2/US15 | game developer | to implement a comprehensive logging system | to track system performance and user interactions. | 3 | KV
2 | SB2/US15 | game developer | to conduct user surveys to gather insights | on the overall gaming experience with the system. | 3 | JS
2 | SB2/US15 | game developer | to create a developer SDK for third-party developers | to build extensions and plugins. | 3 | IK
2 | SB2/US15 | game developer | to continuously update the system | to support new games and features. | 3 | KV
2 | SB2/US15 | game developer | to establish a robust backup and recovery system | to prevent data loss. | 3 | JS
3 | SB2/US15 | game developer | to review and update the project's technical documentation, | it accurately reflects the system's architecture and implementation. | 3 | IK
3 | SB2/US15 | game developer | to create a comprehensive user manual for the AI-powered game controller and interaction system | for the AI-powered game controller and interaction system, so that users can easily understand and use the system. | 3 | KV
3 | SB2/US15 | game developer | to generate a system overview document, outlining the core features and components | stakeholders can get a quick understanding of the project. | 3 | JS
3 | SB2/US15 | game developer | to compile a detailed architecture document, describing | system's design, data flow, and integration points. | 3 | IK
3 | SB2/US15 | game developer | to create a user guide for setting up and configuring the system | system, including step-by-step instructions. | 3 | KV
3 | SB2/US15 | game developer | to prepare a troubleshooting guide | help users resolve common issues they might encounter. | 3 | JS
3 | SB2/US15 | game developer | to generate an API documentation for potential third-party developers, explaining how | integrate their applications with the system. | 3 | IK
3 | SB2/US15 | game developer | to review and refine the project's codebase documentation, | is well-commented and organized. | 3 | KV
3 | SB2/US15 | game developer | to document the system's security measures and best practices | best practices to protect user data and privacy. | 3 | JS
3 | SB2/US15 | game developer | to create a data backup and recovery plan, outlining | safeguard critical project data. | 4 | IK
3 | SB2/US15 | game developer | to generate a detailed system testing report, summarizing the results | testing report, summarizing the results of various testing phases. | 4 | KV
3 | SB2/US15 | game developer | to produce a project completion report, summarizing the entire project journey | the entire project journey, key milestones, and achievements. | 4 | JS
3 | SB2/US15 | game developer | to create a user survey to gather feedback on the system's | gather feedback on the system's usability and performance. | 4 | IK
3 | SB2/US15 | game developer | to design and distribute a feedback form | collect input from project team members regarding their experiences and suggestions. | 4 | KV
3 | SB2/US15 | game developer | to prepare a presentation summarizing the project's goals, methodologies, challenges, and outcomes | potential stakeholders or investors. | 4 | JS
3 | SB2/US15 | game developer | to ensure that all project documentation is up-to-date | reflects the final state of the system. | 4 | IK
3 | SB2/US15 | game developer | o organize a review session with the project team | validate and finalize all documentation. | 4 | KV
3 | SB2/US15 | game developer | to verify that all documents adhere to best practices | technical writing and documentation. | 4 | JS
3 | SB2/US15 | game developer | to create a document storage and version control system | manage all project documentation efficiently. | 4 | IK
3 | SB2/US15 | game developer | to conduct a final review of the user manual to ensure it is user-friendly | ensure it is user-friendly and covers all essential topics. | 4 | KV
3 | SB2/US15 | game developer | to gather testimonials and feedback from users who have tested the documentation | make any necessary improvements. | 4 | JS
3 | SB2/US15 | game developer | to check the accuracy and completeness of the troubleshooting guide | troubleshooting guide, addressing common user issues. | 4 | IK
3 | SB2/US15 | game developer | Manages Different Sections(Reading,Refer,E-Lib) | a clear and in-depth understanding of the system's structure. | 4 | KV
3 | SB2/US15 | game developer | to ensure that the architecture document provides a clear | the API documentation based on potential developer feedback. | 4 | JS
3 | SB2/US15 | game developer | to add any necessary updates | the codebase documentation accurately represents the project's code. | 4 | IK
3 | SB2/US15 | game developer | to perform a final code review | is comprehensive and includes the latest security measures. | 4 | KV
3 | SB2/US15 | game developer | to verify that the security documentation is comprehensive | reliable for potential data loss scenarios. | 4 | JS
3 | SB2/US15 | game developer | o ensure that the backup and recovery plan is robust and reliable | unit, integration, user acceptance | 4 | IK
3 | SB2/US15 | game developer | o create a visually engaging completion report with charts and graphics | highlight project achievements. | 4 | KV
3 | SB2/US15 | game developer | to organize and archive all project documentation in a well-structured | in a well-structured and accessible manner. | 4 | JS
3 | SB2/US15 | game developer | to establish a process for periodic review and update of project documentation | keep it current. | 4 | IK
3 | SB2/US15 | game developer | to share the completed project documentation with relevant | team members. | 4 | KV
3 | SB2/US15 | game developer | to prepare a detailed project presentation, including slides and speaker notes, | for any project review or demonstration. | 4 | JS
3 | SB2/US15 | game developer | to compile all user feedback and suggestions | a feedback analysis report. | 4 | IK
3 | SB2/US15 | game developer | to ensure that the document storage and version control system is accessible | to authorized team members. | 4 | KV
3 | SB2/US15 | game developer | to create a summary document that provides an at-a-glance view of the entire project | at-a-glance view of the entire project for high-level stakeholders. | 4 | JS
3 | SB2/US15 | game developer | to verify that the presentation conveys the project's significance | project's significance and achievements effectively. | 4 | IK
3 | SB2/US15 | game developer | to maintain a system for tracking the usage and effectiveness | he usage and effectiveness of the documentation among end-users. | 4 | KV
3 | SB2/US15 | game developer | to plan for the long-term maintenance and updates | documentation as the project evolves. | 4 | JS
3 | SB2/US15 | game developer | to organize a training session for project team members | users on how to effectively use the documentation. | 4 | IK

## SprintBacklog 1
SPRINT BACKLOG 1
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 1 - <Digital College>
SB1/US1 | As a player, I want the game to recognize and respond to my hand gestures in real-time, allowing for natural and intuitive control. | SB1/US1/T1 | Integrate Mediapipe's pose detection library. | KV+IK+JS | Completed | 2024-01-15
|  | SB1/US1/T2 | Develop the translation mechanism from gestures to in-game actions. | KV | Completed | 2024-01-16
|  | SB1/US1/T3 | Implement a calibration system for gesture precision. | IK | Completed | 2024-01-17
|  | SB1/US1/T4 | Test and refine gesture-based controls. | JS | Completed | 2024-01-20
SB1/US2 | As a player, I want to control the game using voice commands, allowing for a hands-free and dynamic gaming experience. | SB1/US2/T1 | Implement speech recognition using the SpeechRecognition library. | KV+IK+JS | Completed | 2024-01-21
|  | SB1/US2/T2 | Integrate gTTS for natural-sounding responses from the chatbot. | KV | Completed | 2024-01-22
|  | SB1/US2/T3 | Develop a command mapping system for in-game actions. | IK | Completed | 2024-01-23
|  | SB1/US2/T4 | Test voice commands for accuracy and responsiveness. | JS | Completed | 2024-01-24
SB1/US3 | As a player, I want the system to automate certain in-game actions, improving overall responsiveness and control. | SB1/US3/T1 | Gather user feedback on the mu+D12ltiplayer experience.D5:D26 | KV+IK+JS | Completed | 2024-01-25
|  | SB1/US3/T2 | Develop algorithms for precise automation of common gameplay actions. | KV | Completed | 2024-01-26
|  | SB1/US3/T3 | Implement a toggle system for enabling/disabling automation. | IK | Completed | 2024-01-26
|  | SB1/US2/T4 | Test and optimize automated gameplay for various scenarios. | JS | Completed | 2024-01-27
SB1/U4 | As a player, I want an interactive chatbot companion that enhances the gaming experience by providing tips, jokes, and assistance. | SB1/US2/T1 | Develop a chatbot using NLTK for natural language processing. | KV+IK+JS | Completed | 2024-01-27
|  | SB1/US2/T2 | Integrate the chatbot with the gaming system. | KV | Completed | 2024-01-28
|  | SB1/US2/T3 | Implement dynamic responses based on in-game events. | IK | Completed | 2024-01-28
|  | SB1/US2/T4 | Test chatbot interactions and refine responses. | JS | Completed | 2024-01-28
SB1/US5 | As a player, I want the system to support multiplayer interactions, allowing for collaborative or competitive gaming experiences. | SB1/US2/T1 | Implement multiplayer communication protocols. | KV+IK+JS | Completed | 2024-01-29
|  | SB1/US2/T2 | Develop features for gesture and voice interactions in multiplayer mode. | KV | Completed | 2024-01-30
|  | SB1/US2/T3 | Test and optimize multiplayer interactions. | IK | Completed | 2024-01-31
|  | SB1/US2/T4 | Gather user feedback on the multiplayer experience. | JS | Completed | 2024-01-31

## SB BD Ch01
Spring Backlog 01 burn down chart
Date | Planned Total Task | Actual Incompleted Task
2024-01-15 | 132 | 132 | Tasks
2024-01-21 | 100 | 110
2024-01-25 | 50 | 85
2024-01-31 | 30 | 38
Days

## SprintBacklog 2
SPRINT BACKLOG 2
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 2 - <Digital College>
SB2/US1 | As a player, I want an improved calibration system for both gesture and voice controls, ensuring accuracy and personalized experiences. | SB2/D1/T1 | Enhance the gesture calibration algorithm for different hand shapes and sizes. | KV+IK+JS | Completed | 2024-02-01
|  | SB2/D1/T2 | Implement user-specific voice command training for better recognition. | KV | Completed | 2024-02-02
|  | SB2/D1/T3 | Develop a user-friendly calibration interface. | IK | Completed | 2024-02-03
|  | SB2/D1/T4 | Test and gather user feedback on the calibration process. | JS | Completed | 2024-02-04
SB2/US2 | As a player, I want the system to provide dynamic in-game feedback based on my gestures, voice commands, and overall performance. | SB2/D2/T1 | Implement a feedback system that responds to successful gestures and voice commands. | KV+IK+JS | Completed | 2024-02-05
|  | SB2/D2/T2 | Develop visual and auditory cues for feedback. | KV | Completed | 2024-02-05
|  | SB2/D2/T3 | Integrate feedback with the chatbot for a more immersive experience. | IK | Completed | 2024-02-05
|  | SB2/D2/T4 | Test and refine the dynamic feedback system. | JS | Completed | 2024-02-06
SB2/US3 | As a player, I want the system to include accessibility features such as customizable gestures and voice commands to accommodate diverse user needs. | SB2/D3/T1 | Implement customizable gesture mapping. | KV+IK+JS | Completed | 2024-02-08
|  | SB2/D3/T2 | Develop a user-friendly interface for customizing voice commands. | KV | Completed | 2024-02-08
|  | SB2/D3/T3 | Test accessibility features with users who have different needs. | IK | Completed | 2024-02-09
|  | SB2/D3/T4 | Iterate based on user feedback for enhanced accessibility. | JS | Completed | 2024-02-09
SB2/US4 | As a developer, I want to optimize the system's performance using threading for multitasking and improved responsiveness. | SB2/D4/T1 | Identify key areas for implementing threading. | KV+IK+JS | Completed | 2024-02-11
|  | SB2/D4/T2 | Implement threading for parallel execution of non-blocking tasks. | KV | Completed | 2024-02-11
|  | SB2/D4/T3 | Optimize resource-intensive processes for smoother multitasking. | IK | Completed | 2024-02-12
|  | SB2/D4/T4 | Test and profile the system for performance improvements. | JS | Completed | 2024-02-13
SB2/US5 | As a user, I want comprehensive documentation and a user guide to understand how to set up and use the AI-powered game controller and interaction system. | SB2/D5/T1 | Write detailed documentation on system architecture and components. | KV+IK+JS | Completed | 2024-02-14
|  | SB2/D5/T2 | Create a step-by-step user guide for setting up and configuring the system. | KV | Completed | 2024-02-15
|  | SB2/D5/T3 | Include troubleshooting tips and FAQs. | IK | Completed | 2024-02-16
|  | SB2/D5/T4 | Collect user feedback on documentation and refine accordingly. | JS | Completed | 2024-02-16
0

## SB BD Ch02
Spring Backlog 02 burn down chart
Date | Planned Total Task | Actual Uncompleted Task
2024-02-01 | 177 | 190 | Tasks
2024-02-08 | 110 | 150
2024-02-13 | 80 | 100
2024-02-16 | 66 | 65
0
Days

## SprintBacklog 3
SPRINT BACKLOG 3
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 3 - <Digital College>
SB3/US1 | As a developer, I want to make a exe file Research PyInstaller and cx_Freeze for converting .py to .exe. | SB3/US2/T1 | Investigate cx_Freeze features and compatibility. | KV+IK+JS | Completed | 2024-07-01
|  | SB3/US2/T2 | Implement event tracking for user interactions. | KV | Completed | 2024-10-01
|  | SB3/US2/T3 | Explore PyInstaller documentation and tutorials. | IK | Completed | 2024-12-01
|  | SB3/US2/T4 | Discuss pros and cons of each tool with the team. | JS | Completed | 15/1/2024
SB3/US2 | As a player, I want the game environments to dynamically respond to my gestures and voice commands, Convert .py Files to .exe. | SB3/US2/T1 | Decide on the preferred tool based on research findings and team consensus. | KV+IK+JS | Completed | 17/1/2024
|  | SB3/US2/T2 | Evaluate ease of use, community support, and compatibility. | KV | Completed | 20/1/2024
|  | SB3/US2/T3 | Address any errors or warnings encountered during the conversion process. | IK | Completed | 22/1/2024
|  | SB3/US2/T4 | Ensure compatibility with different operating systems (OS). | JS | Completed | 24/1/2024
SB3/US3 | As a security-conscious player, Research System-Independent File Handling | SB3/US2/T1 | Investigate methods for achieving system-independent file execution. | KV+IK+JS | Completed | 25/1/2024
|  | SB3/US2/T2 | Research containerization techniques for Python applications. | KV | Completed | 27/1/2024
|  | SB3/US2/T3 | Provide recommendations for the team based on research outcomes. | IK | Completed | 28/1/2024
|  | SB3/US2/T4 | fixed error | JS | Completed | 30/1/2024
SB3/US4 | Fix Bugs and Implement Threading for Mic and Audio Functions | SB3/US2/T1 | Identify and prioritize bugs in the current system. | KV+IK+JS | Completed | 2024-04-02
|  | SB3/US2/T2 | Debug the codebase to pinpoint and classify existing bugs. | KV | Completed | 2024-05-02
|  | SB3/US2/T3 | Develop solutions for critical bugs identified in the previous step. | IK | Completed | 2024-07-02
|  | SB3/US2/T4 | Verify bug fixes through rigorous testing. | JS | Completed | 2024-12-02
SB3/US5 | Implement threading for microphone and audio functions. | SB3/US2/T1 | Review existing codebase for mic and audio functionalities. | KV+IK+JS | Completed | 17/2/2024
|  | SB3/US2/T2 | Integrate threading concepts to enable concurrent processing. | KV | Completed | 21/2/2024
|  | SB3/US2/T3 | Test the threaded functions to ensure performance improvements and stability. | IK | Completed | 25/2/2024
|  | SB3/US2/T4 | run and test | JS | Completed | 29/2/2024

## SB BD Ch03
Spring backlog 3 Burnt Down chart
Date | Planned Total Task | Actual Uncompleted Task
2017-10-12 | 177 | 190 | Tasks
2017-10-24 | 110 | 150
2017-10-26 | 80 | 100
2017-10-28 | 25 | 17
2017-11-01 | 15 | 15
2017-11-02 | 0 | 0
0
Days

## SprintBacklog 4
SPRINT BACKLOG 4
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 4 - <Digital College>
SB4/US1 | Plan Execution and Documentation | SB4/US2/T1 | Define project scope and objectives. | KV+IK+JS | Completed | 29/2/2024
|  | SB4/US2/T2 | Create a timeline for development and reporting. | KV | Completed | 2024-01-03
|  | SB4/US2/T3 | Outline tasks for implementation using Tkinter, report creation, research paper writing, and publication strategy. | IK | Completed | 2024-03-03
|  | SB4/US2/T4 | Allocate resources and assign responsibilities to team members | JS | Completed | 2024-05-03
SB4/US2 | Implement GUI using Tkinter | SB4/US2/T1 | Design GUI layout and components. | KV+IK+JS | Completed | 2024-07-03
|  | SB4/US2/T2 | Integrate functionality with GUI elements. | KV | Completed | 2024-09-03
|  | SB4/US2/T3 | Test GUI interactions for usability and functionality. | IK | Completed | 2024-11-03
|  | SB4/US2/T4 | Optimize GUI performance and aesthetics based on feedback. | JS | Completed | 13/3/2024
SB4/US3 | Research Paper Development | SB4/US2/T1 | Conduct literature review on relevant topics. | KV+IK+JS | Completed | 14/3/2024
|  | SB4/US2/T2 | Summarize project methodology and findings. | KV | Completed | 14/3/2024
|  | SB4/US2/T3 | Draft, revise, and finalize the research paper. | IK | Completed | 15/3/2024
|  | SB4/US2/T4 | Ensure proper citation and adherence to academic standards. | JS | Completed | 16/3/2024
SB4/US3 | Project Report Creation | SB4/US2/T1 | Gather project documentation and results. | KV+IK+JS | Completed | 17/3/2024
|  | SB4/US2/T2 | Structure the report according to standard format. | KV | Completed | 18/3/2024
|  | SB4/US2/T3 | Review and edit the report for clarity and coherence. | IK | Completed | 19/3/2024
|  | SB4/US2/T4 | Include visual aids and supplementary materials to enhance understanding. | JS | Completed | 19/3/2024
SB4/US5 | Research Paper Publication | SB4/US2/T1 | Identify suitable journals or conferences for submission. | KV+IK+JS | Completed | 19/3/2024
|  | SB4/US2/T2 | Format the paper according to publication guidelines. | KV | Completed | 20/3/2024
|  | SB4/US2/T3 | Submit the paper and track its progress through the review process. | IK | Completed | 20/3/2024
|  | SB4/US2/T4 | Address reviewer comments and prepare for final publication. | JS | Completed | 20/3/2024

## SB BD Ch04
Date | Planned Total Task | Actual Uncompleted Task
29/2/2024 | 177 | 190 | Tasks
2017-10-24 | 110 | 150
2017-10-26 | 80 | 100
2017-10-28 | 25 | 16
2017-11-01 | 15 | 15
20/3/2024 | 0 | 0
0
Days